## ETL
[6 empty] | Check list |  | Where | S | Comment
Key | Summary
C165366-1880 | Develop loaders for new DSMT MLE and CLE codes
| Issue Type | Priority | Assignee | Component/s | Due Date | 1 | MDD | SP
| Improvement | High | Li Li | ETL, UI | 2017-02-23 | 2 | Test Plan | SP
[6 empty] | 3 | Test Cases | SP
[6 empty] | 4 | Code | SVN
[6 empty] | 5 | SQL | No
[6 empty] | 6 | Real Data | PROD server |  | Month end -2 day from CDA, in that day, need to contact to Product Support team to Copy them and test.
Key | Summary
C165366-1798 | Error message that “index in an unusable state” is not a legitimate reason for failure of the data edits.
[6 empty] | 1 | Code | SVN
| Issue Type | Priority | Assignee | Component/s | Due Date | 2 | Store Procedure | DB |  | The SP will be created by Vishad, Next Wednesday I need to contact Vishad and ask him for it, And I will do the testing.
| Defect | Major | Vishad | RUBY Database | 2017-03-23 | 3 | test cases - ETL side | SP
Key | Summary | [8 empty] | Postpone, after 1881 is done
C165366-1731 | Table design for few of the process on how logs are maintained and blocks on UI.
| Issue Type | Priority | Assignee | Component/s | Due Date | 1 | Design | Draft |  | Need to make a design to how to merge this 3 tables into one.
| Defect | Medium | me | ETL, UI | 2017-03-16 | 2 | Negotiation | Email |  | After desgin, need to
[6 empty] | 3 | Make a deal | Email |  | With UI team and ETL team.
[6 empty] | 4 | Code | SVN
[6 empty] | 5 | Db change, SQL | DB, SVN |  | Maybe from DB team, or by myself, should contains in email. ¦ need to discuss with Lily.
[6 empty] | 6 | Test Cases | SP