## ETL maintain - Mar
[6 empty] | Check list |  | Where | S | Comment
Key | Summary
C165366-1880 | Develop loaders for new DSMT MLE and CLE codes
| Issue Type | Priority | Assignee | Component/s | Due Date | 1 | MDD | SP
| Improvement | High | Li Li | ETL, UI | 2017-02-23 | 2 | Test Plan | SP
[6 empty] | 3 | Test Cases | SP
[6 empty] | 4 | Code | SVN
[6 empty] | 5 | SQL | SVN |  | Need to create SQL
[6 empty] | 6 | Real Data | PROD server |  | Month end -2 day from CDA, in that day, need to contact to Product Support team to Copy them and test.
[6 empty] | 7 | Cooperate with UI team |  |  | Work with UI team to confirm if the UI code is reverted.
Key | Summary
C165366-1798 | Error message that “index in an unusable state” is not a legitimate reason for failure of the data edits.
[6 empty] | 1 | Code | SVN
| Issue Type | Priority | Assignee | Component/s | Due Date | 2 | Store Procedure | DB |  | The SP will be created by Vishad, Next Wednesday I need to contact Vishad and ask him for it, And I will do the testing. 0227 Vishad: the scpirt will be ready by tomorrow.
| Defect | Major | Vishad | RUBY Database | 2017-03-23 | 3 | test cases - ETL side | SP
Key | Summary | [8 empty] | Postpone, after 1881 is done. ¦ I have a draft, a part, in the notebook.
C165366-1731 | Table design for few of the process on how logs are maintained and blocks on UI.
| Issue Type | Priority | Assignee | Component/s | Due Date | 1 | Design | Draft |  | Need to make a design to how to merge this 3 tables into one.
| Defect | Medium | me | ETL, UI | 2017-03-16 | 2 | Negotiation | Email |  | After desgin, need to
[6 empty] | 3 | Make a deal | Email |  | With UI team and ETL team.
[6 empty] | 4 | Code | SVN
[6 empty] | 5 | Db change, SQL | DB, SVN |  | Maybe from DB team, or by myself, should contains in email. ¦ need to discuss with Lily.
[6 empty] | 6 | Test Cases | SP
Key | Summary
C165366-1884 | Remove the mapping for the index_pay field from both CPS and PHY
| Issue Type | Priority | Assignee | Component/s | Due Date | 1 | Code | SVN
| Defect | Medium | me | ETL | 2017-03-23 | 2 | Test Cases | SP |  | Maybe need to add some more test cases for it. Evidents in there is not matched, need a more perfect one.
Key | Summary | [8 empty] | Li Li let me test and write the test cases and MDD.
C165366-1853 | Process Change to ETL jobs
| Issue Type | Priority | Assignee | Component/s | Due Date | 1 | MDD
| Improvement | Medium | Li Li | ETL | 2017-03-30 | 2 | Test Plan
[6 empty] | 3 | Code |  |  | Li Li is done this part.
[6 empty] | 4 | Test Cases
[6 empty] | 5 | User Approval
Key | Summary
C165366-1796 | Remove odd transactions in PHY
| Issue Type | Priority | Assignee | Component/s | Due Date | 1 | MDD
| Improvement | Medium | me | ETL, UI | 2017-03-30 | 2 | Test Plan
[6 empty] | 3 | Code
[6 empty] | 4 | Test Cases
[6 empty] | 5 | Cooperate with UI team |  |  | UI need a plan, I need to tell them what is needed.
[6 empty] | 6 | Integration testing
[6 empty] | 7 | Negotiation |  |  | with Leonid
Key | Summary
C165366-1856 | Show Error Message in ETL Job Report When Caused by Hierarchy Service.
| Issue Type | Priority | Assignee | Component/s | Due Date
| Improvement | Medium | Li Li | ETL | 2017-03-30

## ETL Model Assignment
[6 empty] | Check list | Where | S | Comment
Key | Summary
C165366-1881 | Operationalize model assignment setups as unique blocks of assignments | [7 empty] | 7. Approve/reject a block ¦ ETL_USER_DETAIL table merge
| Issue Type | Priority | Assignee | Component/s | Due Date
| New Feature | Major | Vamsi | Analytics, ETL, DB, UI | 2017-04-27

## Comment
DONE | PARTIAL | DOING | TO DO | POSTPONE | NEED PLAN | MAY